## Sheet1
ID	Work Package	CW50	CW51	CW52	CW01	CW02	CW03	CW04	CW05	CW06	CW07	CW08	CW09	CW10
1	Project Plan	S / J (21.12.)
1.1	Brief Description	S
1.2	Demands	S
1.3	Substeps	J
1.4	Schedule	J
2	Holiday			S / J
3	Conceptual Design				S / J
4	Interim Report						S / J (19.01.)
5	Development					S / J	S / J	S / J	S / J
5.1	Code Structur					S / J
5.2	Functions						S / J	S / J
5.3	Implementation								S / J
6	Debugging										S / J
7	Final Report											S / J (07.03.)
8	Documentation				S / J	S / J	S / J	S / J	S / J	S / J
9	Backup													S / J